{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["汇总","总控系统报价单 ","硬件报价"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"汇总","index":0,"n_rows":18,"n_cols":11,"rows_kept":18,"cut":false,"hidden":false,"merged":[[0,0,0,8],[3,1,3,2],[4,1,4,2],[5,1,5,2],[6,1,6,2],[7,1,7,2],[8,1,8,2],[9,1,9,2],[1,0,2,0],[4,0,8,0],[1,5,2,5],[3,5,9,5],[7,6,8,6],[7,7,8,7],[7,8,8,8],[7,9,8,9],[4,10,9,10],[3,3,9,4],[1,1,2,2],[1,3,2,4]]}
["宝霆智能平台研发计划"]
["类型","详细内容",null,"开始时间",null,"结束时间","第1节点","第2节点","第3节点","第4节点","第4节点"]
[{"$nulls":6},"2022-01-14","2022-01-25","2022-02-19","2022-02-25","2022-02-28"]
["说明",null,null,"2021-12-16",null,"2022/02/30","系统简单串联。\n在系统可以看见设备在线离线，","功能开发、开始调试。\n用户通过账号密码可以下单，硬件收到生产指令。","完善边角功能，调试","可用","交付、客户联调"]
["系统研发","安卓端研发（含硬件）",{"$nulls":4},"1、安卓端先做界面、\n2、做简单接口对接","1、对接服务端接口做功能，\n2、传递设备信息给服务端","调试接口","整体调试","客户联调"]
[null,"PLC控制系统研发（含硬件）",{"$nulls":4},"1、硬件设计调试\n2、给安卓一些接口数据。如：设备在线离线接口。\n硬件控制这块，20天有交付东西李老师负责，和客户沟通硬件对接出一个计划，","1、设备可以通过PLC独立控制使用\n2、给安卓端全部接口\n3、硬件独立调试、部分可通过接口安卓调试","整体调试","整体调试"]
[null,"后台服务端研发",{"$nulls":4},"1.框架基础功能集成模型管理、生产资源管理。\n2、在线离、分销层级、产品、工艺\n3、给安卓部分接口","1、持续功能开发\n3、给安卓接口\n4、支持安卓调试","完善边角、调试","完善边角、调试"]
[null,"用户小程序端研发",{"$nulls":4},"小程序考虑先做成h5，账号密码登录，后期对接小程序","1、开发业务功能","1.对接小程序\n2、对接支付接口\n3、对接登录接口\n4，完善部分业务","1.对接小程序\n2、对接支付接口\n3、对接登录接口\n4，完善部分业务"]
[null,"运维小程序"]
["系统联调","安卓端、PLC控制系统、服务器端整体联调",{"$nulls":5},"开始联调","开始联调","开始联调"]
[]
[]
[]
[]
[]
[null,"需求--讨论设计"]
[null,"支付接口、登录接口"]
[null,"支付宝、微信"]

{"sheet":"总控系统报价单 ","index":1,"n_rows":8,"n_cols":6,"rows_kept":8,"cut":false,"hidden":true,"merged":[[0,0,0,5],[1,1,1,2],[1,3,1,4],[2,1,2,2],[2,3,2,4],[3,1,3,2],[3,3,3,4],[4,1,4,2],[4,3,4,4],[5,1,5,2],[5,3,5,4],[6,1,6,2],[7,0,7,4]]}
["金科力柔性制造生产线智能总控系统报价"]
["类型","详细内容",null,"说明",null,"合计\n（万元）"]
["硬件定制"]
["软件系统"]
["系统联调"]
["系统实施与培训","知识库培训，会议培训","系统部署实施、系统上线运行、系统培训"]
["系统维护","系统日常使用维护",null,"第一年免费，第二年协商决定"]
["总计"]

{"sheet":"硬件报价","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[[0,0,0,5],[1,1,1,2],[1,3,1,4],[2,1,2,2],[2,3,2,4],[3,1,3,2],[3,3,3,4],[4,1,4,2],[4,3,4,4],[5,0,5,4]]}